**South Dakota MTSS**

**2024-25 Evaluation Plan**



The South Dakota MTSS (Multi-Tiered Systems of Support) initiative focuses on two areas:

1. **MTSS Academics is referred to as RtI (Response to Intervention):** Improve reading results for students through teacher training, instructional coaching, evidence-based practices, and tiered intervention supports.
2. **MTSS-Behavior is referred to as PBIS (Positive Behavioral Interventions and Supports):** Provide supports through MTSS+ for students’ behavioral and mental wellness.

Due to the nature of each respective initiative, some evaluation components will focus on one initiative. For more information about which evaluation components your district will complete, please see the “Which Schools?” question under each evaluation component.

|  |
| --- |
| **A. Evaluations Related to Professional Development** |
| 1. **Training Tracking**   **What?** Each training will be entered into a web-based tracking system: South Dakota Professional Development (SDPD) website.  **Why?** To keep track of the number and type of trainings that have been administered and to keep track of evaluations and participants  **Which Schools?** RtI and PBIS  **Who Completes?**  Coordinators/Coaches/State Staff  **When?** Ongoing  **How?** SDPD website logins will be given to State staff and Coordinators/Coaches: <https://sdpd.ddehome.com/> |
| 1. **Sign-In Sheet**   **What?** All participants from each training will be uploaded into SDPD.  **Why?** To track # of participants in the trainings; to use for follow-up surveys  **Which Schools?** RtI and PBIS  **Who Completes?** Coordinators/Coaches/State Staff  **When?** At each training  **How?** On paper, transferred to spreadsheet then uploaded to the SDPD website: <https://sdpd.ddehome.com/> |
| 1. **End-of-PLD Questionnaire**   **What?** Evaluation of the trainings  **Why?** To determine how satisfied participants are with the training and how useful participants perceive the training to be  **Which Schools?** RtI and PBIS  **Who Completes?** Participants at each of the trainings  **When?** After each training  **How?** A unique URL through the SDPD website to the evaluation form will be given to participants after each training |
| 1. **Focus Groups/Interviews (Teachers, Coaches, and Coordinators)**   **What?** Focus group (in-person or virtual) or phone interviews (conducted every other year) of teachers, coaches, and coordinators.  **Why?** To get qualitative and detailed information regarding the extent to which participants are implementing the skills they learned in the trainings and the extent to which they are satisfied with the trainings  **Which Schools?** RtI and PBIS  **Who Completes? For focus groups:** Sample of 2-3 MTSS schools, coaches, and coordinators.  **For interviews:** Sample of MTSS school teachers, coaches, and coordinators.  **When?** Focus groups in spring 2025 (Interviews in spring 2026)  **How?**  **For focus groups:** Data Driven Enterprises (DDE) will visit each selected school and interview the team in a group setting. Coach and coordinator focus groups will be conducted virtually.  **For interviews:** DDE will conduct the phone interviews with individual participants. |

|  |
| --- |
| **B. Evaluations Related to Literacy/Instruction** |
| 1. **Reading Tiered Fidelity Inventory (R-TFI)**   **What?** Rubric to monitor fidelity of RtI implementation.  **Why?** To determine if RtI is being implemented with fidelity  **Which Schools?** RtI Only  **Who Completes?** Team members at each school who are responsible for monitoring school-level fidelity of MTSS implementation.  **When?** Spring 2025  **How?** Teams will complete the R-TFI and record results in the provided spreadsheet. An electronic file uploaded to the secure Dropbox link:  <https://www.dropbox.com/request/BFW9HuniqGlzeo4wfINj> |
| 1. **Classroom Observation Checklist**   **What?** Checklist of explicit instruction skills and core literacy strategies observed during a lesson  **Why?** To determine if instructional staff are implementing explicit instruction and core literacy strategies with fidelity  **Which Schools?** RtI Only  **Who Completes?** The coaches/coordinators will observe 20% of participating teachers  **When?** Spring 2025  **How?** Online via Alchemer: <https://survey.alchemer.com/s3/6436953/SDobschecklist> |
| 1. **Foundational Literacy Training Pre-/Post-Test *(2025-26 School Year – No Trainings in 2024-25)***   **What?** A pre-/post-test for foundational literacy trainings will be administered.  **Why?**  To determine the extent to which the participants learn new knowledge.  **Which Schools?** RtI Only  **Who Completes?**  Participants at literacy trainings  **When?** At the beginning of literacy trainings and at the end of literacy trainings.  **How?** Online via Alchemer: <https://survey.alchemer.com/s3/6437351/SDprepost> |

|  |
| --- |
| **C. Evaluations Related to Behavior** |
| 1. **Tiered Fidelity Inventory (TFI) – Behavior**   **What?** Rubric to monitor fidelity of PBIS implementation  **Why?** To determine if PBIS is being implemented with fidelity  **Which Schools?** PBIS Only  **Who Completes?** Team members at each school who are responsible for monitoring school-level fidelity of PBIS implementation.  **When?** Spring 2025  **How?** Teams will complete the TFI on the PBIS Center website: <https://www.pbisapps.org> |
| 1. **ODR Data**   **What?** ODR, suspension/expulsion, attendance, chronic attendance, and youth risk indicators (kids count) data  **Why?** To determine if students’ behavior changes from fall to spring and from one year to the next  **Which Schools?** PBIS Only  **Who Completes?**  PBIS coordinators  **When?** December 2024 and May 2025  **How?** Two options. An electronic file uploaded to the secure Dropbox link: <https://www.dropbox.com/request/BFW9HuniqGlzeo4wfINj>  **Option 1:** Download data from SWIS (or other behavior tracking system) and upload to Dropbox.  **Option 2:** Complete the ODR Data Inventory spreadsheet and upload to Dropbox. |
| 1. **School** **Climate Survey (for students and staff)**   **What?** Survey about the climate of the school  **Why?** To determine student and staff perceptions of school climate; to compare staff perceptions to student perceptions  **Which Schools?** PBIS Only  **Who Completes?** Students and staff members at participating PBIS schools  **When?** Spring 2025 (January-May)  **How?** An online survey link via Alchemer will be given to students:  **Students Grades 3-5:** <https://survey.alchemer.com/s3/5171397/SDMTSSclimatestudent35>  **Students Grades 6-12:** <https://survey.alchemer.com/s3/6845657/SDMTSSclimatestudent612>  **Staff:** <https://survey.alchemer.com/s3/5169263/SDMTSSclimatestaff> |

|  |
| --- |
| **D. Evaluations Related to Coaches and Coordinators** |
| 1. **Coaching Survey**   **What?** A questionnaire that measures satisfaction with the coaching activities provided to districts and schools.  **Why?** To determine the effectiveness of the coaching  **Which Schools?** RtI  **Who Completes?** Staff members (all general education and special education teachers in the school) who received coaching  **When?** Due byMay 15, 2025  **How?** Coaches will send a link to the online survey via Alchemer to staff members: <https://survey.alchemer.com/s3/6438978/SDcoachingsurvey> |
| 1. **Coordinator Survey**   **What?** A survey about the effectiveness of the coordinator  **Why?** To determine the effectiveness of the coordinator  **Which Schools?** RtI and PBIS  **Who Completes?** Staff members at schools that participated in the MTSS project during the 2023-24 school year  **When?** Due byMay 15, 2025  **How?**  An online survey link via Alchemer will be given to staff members: <https://survey.alchemer.com/s3/5167385/SDMTSScoordinatorsurvey> |

|  |
| --- |
| **E. Evaluations Related to Framework/Leadership** |
| 1. **Sustainability Survey**   **What?** Written questionnaire  **Why?** To collect feedback on the sustainability of the projects  **Which Schools?** RtI and PBIS  **Who Completes?** Teachers, coaches, coordinators, principals, district leads, and superintendents  **When?** January/February 2025  **How?** Online via Alchemer: <https://survey.alchemer.com/s3/7085169/SDMTSSSustainabilitySurvey> |

|  |
| --- |
| **F. Evaluations Related to Family Engagement** |
| 1. **Family Engagement Survey**   **What?** Written questionnaire about the extent to which the school encourages family involvement  **Why?** To measure family engagement  **Which Schools?** RtI Only  **Who Completes?** Family members and educators at RtI schools  **When?** Due byMay 15, 2025  **How?** Online via Alchemer:  **Family Members:** <https://survey.alchemer.com/s3/6440499/SDfamilysurvey>  **Educators:** <https://survey.alchemer.com/s3/6440572/SDeducatorsurvey> |

|  |
| --- |
| **G. Student Data** |
| 1. **Benchmark Data**   **What?** Reading benchmark data  **Why?** To determine if students’ scores increase from fall to spring and from one year to the next  **Which Schools?** RtI Only  **Who Completes?** DDE will calculate based on the benchmark data files provided to them bydistricts  **When?** Three times per year (fall data by October 1, winter data by February 1, and spring data by June 1)  **How?** An electronic file with student ID number and test scores uploaded to the secure Dropbox link: <https://www.dropbox.com/request/BFW9HuniqGlzeo4wfINj> |
| 1. **State Test Data**   **What?** Reading achievement data on the state test  **Why?** To determine if students’ scores increase from one year to the next  **Which Schools?** RtI and PBIS  **Who Completes?** DDE will calculate based on the assessment file provided to them bySD DOE  **When?** Summer 2025  **How?** An electronic file with student ID number and test scores |
| 1. **Student LRE Data**   **What?** Student environment placement (e.g., in regular classroom 80% or more; in regular classroom 40-79%, etc.) as indicated on the Child Count Placement file.  **Why?** To determine if student placement changes over time  **Which Schools?** RtI Only  **Who Completes?** DDE will calculate based on the child count file provided to them bySD DOE  **When?** January 2025  **How?** An electronic file with student ID number and environment code |

Data Driven Enterprises (DDE) is collecting and analyzing the evaluation information.

Amy Lance, Project Director, [amy@datadrivenenterprises.com](mailto:amy@datadrivenenterprises.com), 907-250-6208

Susan Wagner, President, [susan@datadrivenenterprises.com](mailto:susan@datadrivenenterprises.com), 303-255-4648